## Project Details
Project Objectives | The objective of this project is to develop and complete the construction of 20 terrace residential house units, including all associated structural, architectural, civil, mechanical, electrical, plumbing, and external works, in compliance with approved drawings, statutory regulations, and project quality standards, and to achieve timely handover within the authorized budget and project timeline.
Project description | This project comprises the planning, coordination, and construction of 20 units of terrace residential houses, together with all associated civil, structural, architectural, mechanical, electrical, plumbing, and external infrastructure works necessary to achieve full completion and readiness for handover. The works shall be executed in accordance with approved drawings, technical specifications, applicable statutory and regulatory requirements, quality standards, and health, safety, and environmental obligations. The project includes all activities required from pre-construction mobilization through construction, inspection, testing, commissioning where applicable, and final completion, including the provision of labor, materials, equipment, supervision, and site management. The intended outcome is the successful delivery of 20 completed terrace residential units and associated supporting works within the approved project timeline and budget, and in a condition suitable for inspection, approval, and handover to the client or end users.
Outline of Scope of Work | The scope of work for this project includes the execution and completion of all works required for the construction of the 20 terrace residential units. This includes pre-construction and site mobilization, such as site establishment, temporary facilities, site hoarding, access arrangements, setting out, and mobilization of personnel, equipment, and materials. It includes (a) site preparation and earthworks, covering clearing, grubbing, excavation, filling, leveling, compaction, and any required ground preparation works for the housing development. (b) substructure and foundation works, such as excavation for foundations, footings, foundation concrete, ground beams, slab-on-grade works, waterproofing, and other related underground structural components. (c) superstructure works, covering columns, beams, suspended slabs, load-bearing walls, staircases, and all structural framework necessary for the terrace houses. (d) roofing works, including roof structure, roof coverings, insulation where specified, rainwater goods, flashing, and associated accessories. (e) architectural and building works, such as masonry, partitions, plastering, screeding, ceiling works, doors, windows, glazing, ironmongery, and all general building finishes required by the approved design. (f) mechanical, electrical, and plumbing works, including internal wiring, power distribution, lighting points, water supply piping, sanitary plumbing, drainage piping, fixtures installation, and associated service connections required for each unit. (g) internal and external finishes, such as wall finishes, floor finishes, painting, fittings, fixtures, cabinetry or built-in items where specified, and all finishing works necessary to achieve the required quality standard.
(h) external works and infrastructure, such as internal roads, drains, walkways, parking areas, boundary elements if included in the approved design, utility connections, landscaping, and other supporting external works serving the residential units. (i) testing, inspection, approvals, and rectification, covering statutory inspections, quality inspections, testing of installed systems, correction of defects, and compliance activities required for practical completion. (j) handover and closeout, including final cleaning, as-built documentation where required, defect listing, completion records, and formal handover of the completed units to the client.
Scope Boundries | The project scope covers the construction and completion of 20 terrace residential house units and all associated works expressly indicated in the approved drawings, specifications, and contract documents. Any works not identified in the approved design documents, contract conditions, or statutory requirements shall be treated as outside the project scope unless formally approved through change control.
Scope Inclusions | The project scope includes the planning, coordination, construction, testing, completion, and handover of 20 units of terrace residential houses on the designated greenfield site in Precinct 19, Putrajaya, together with all associated works expressly identified in the approved drawings, specifications, and contract documents. Included works comprise site possession, mobilization, temporary site facilities, site establishment, hoarding, temporary access, setting out, and all pre-construction activities necessary to commence and manage the works. The scope also includes land clearing, grubbing, earthworks, excavation, filling, leveling, compaction, and other ground preparation works required to make the site suitable for construction. The scope includes substructure and foundation works, including excavation for foundations, footings, ground beams, slabs, waterproofing, and all related structural base elements. It also includes all superstructure works required for the terrace houses, including reinforced concrete or other approved structural elements, walls, columns, beams, slabs, staircases, roof structures, roof coverings, and associated building components. Included architectural works comprise masonry, partitions, plastering, screeding, ceilings, doors, windows, glazing, ironmongery, internal finishes, external finishes, painting, fittings, fixtures, and all other finishing works specified in the approved design documents. Mechanical, electrical, and plumbing works are included, covering electrical wiring, lighting, distribution boards, water supply piping, sanitary plumbing, sewerage reticulation within the site boundary, drainage systems, and installation of required fixtures and fittings.
The scope includes external and ancillary works necessary to support the residential development as shown in approved design documents, such as internal roads, accessways, walkways, surface drainage, perimeter drains, utility corridors within the project boundary, parking areas if specified, boundary treatments if specified, and landscaping works identified in the approved scope. The project also includes testing, inspections, rectification of defects identified prior to completion, statutory compliance activities, completion documentation, and formal handover of the completed houses. Because the site is a greenfield location near Putrajaya Lake, included scope also extends to temporary erosion and sediment control measures, construction-phase drainage management, site runoff control, environmental protection measures required by approvals, and site protection provisions necessary to prevent adverse impact on adjacent land and nearby water-sensitive areas.
Scope Exclusions | The project scope excludes any land acquisition, land title regularization, rezoning, or legal settlement matters unless expressly stated in the contract or employer’s requirements. It excludes off-site infrastructure upgrades beyond the project boundary unless specifically identified in the approved drawings or imposed as a formal condition of approval and incorporated into the contract scope. The scope excludes major utility reinforcement works by external service providers outside the site boundary, including upstream electrical substations, trunk water mains, regional sewer upgrades, telecommunications backbone works, or public road widening works, except for normal connection interface works expressly assigned to the contractor under the contract documents. It excludes sales, marketing, financing, property management, leasing, and end-buyer customization unless explicitly included. It also excludes loose furniture, movable appliances, and non-fixed owner-supplied items unless these are specifically listed in the contract requirements. The scope excludes future expansion works, additional housing units beyond the 20 terrace houses, community facilities not shown on approved drawings, and any aesthetic or design upgrades requested after approval unless processed through formal change control. Remediation of unforeseen contamination, unusual ground conditions, archaeological findings, or protected ecological features is excluded except to the extent specifically covered by contingency provisions or contract terms. The scope also excludes post-handover operation and maintenance services other than the defects liability obligations stated in the contract. Any works outside the approved project boundary, or not expressly required by the contract documents, statutory conditions, or approved design, shall be deemed outside the project scope unless formally authorized.
Project Assumptions | It is assumed that the project site in Precinct 19 is legally available for development and designated or approvable for the intended residential use under the relevant planning and land-use controls. It is assumed that all required project approvals, permits, and consents from the relevant authorities will be obtainable within the planned timeframe and without materially changing the base project scope. It is assumed that the geotechnical condition of the greenfield site will be reasonably consistent with available preliminary site information and suitable for the proposed terrace housing development using conventional foundation solutions, unless subsequent investigation indicates otherwise. It is also assumed that no extraordinary subsurface obstructions, contamination, or unstable soil conditions will be encountered beyond what is typical and manageable under normal construction practice. It is assumed that access to the site will be available for construction vehicles, plant, materials, and labor throughout the project duration, subject to normal regulatory and traffic restrictions. It is assumed that utility connection points for water, electricity, drainage, sewerage, and telecommunications will be available within a practical distance and can be connected within the project schedule. It is assumed that the approved design, employer requirements, and technical specifications will be sufficiently complete and coordinated before major construction activities begin, and that stakeholder decisions, approvals of materials, and consultant responses will be provided within agreed turnaround times. It is further assumed that weather conditions will remain within normal seasonal patterns for the area and will not cause prolonged abnormal disruption beyond reasonable schedule allowances. Because the site is near Putrajaya Lake, it is assumed that required environmental protection measures, stormwater controls, and runoff mitigation systems can be designed and implemented in a manner acceptable to the relevant authorities without requiring substantial redesign of the project. It is also assumed that neighboring land uses and authority conditions will permit construction to proceed under standard working-hour and environmental management controls.
Project Constraints | The project is constrained by the approved budget, contract duration, available resources, and the need to deliver all 20 units within the authorized cost and schedule baseline. It is constrained by compliance with approved drawings, technical specifications, local planning conditions, statutory permits, building regulations, health and safety requirements, and applicable environmental obligations. The greenfield nature of the site creates constraints related to initial site access, temporary utilities, earthworks management, drainage formation, and early-stage infrastructure readiness. The proximity to Putrajaya Lake introduces heightened constraints on erosion control, sediment management, stormwater runoff, water-sensitive environmental protection, and possibly restrictions on certain construction activities, discharge practices, and site disturbance methods. The project may also be constrained by permit approval lead times, utility provider response times, inspection hold points, material availability, labor supply, and limitations on heavy vehicle movement or working hours imposed by authorities or surrounding development conditions. Weather, especially periods of heavy rain, may constrain excavation, earthworks, drainage installation, and external works. The site layout and development density may constrain staging areas, storage zones, internal traffic circulation, and simultaneous work fronts. In addition, any late design changes, authority-imposed conditions, or unexpected subsurface findings may constrain productivity and impact schedule and cost performance.

## CDM1
Project Name:
Revision Number:
Date:
1.0 Project CDM Strategy Brief (CDM1)
Information Status
| CDM Strategy Brief | Team Responses to Project Leader | Comments - Contacts details, Notes, Dates Reviews, etc. | Required | Received
1.1 | Project Details
| 1.1.1. Description of project | This project comprises the planning, coordination, and construction of 20 units of terrace residential houses, together with all associated civil, structural, architectural, mechanical, electrical, plumbing, and external infrastructure works necessary to achieve full completion and readiness for handover. The works shall be executed in accordance with approved drawings, technical specifications, applicable statutory and regulatory requirements, quality standards, and safety and health, and environmental obligations. |  | TRUE | FALSE
| 1.1.2. Scope of works |  |  | FALSE | TRUE
| 1.1.3. Address/ location/ environment of site |  |  | TRUE | FALSE
1.2 | Client Brief/ Outline CDM Scope
| 1.2.1. Operational requirements | For example, any existing activities to remain e.g. Occupation, Manufacture, etc. Whether or not the structure will be used as a place of work. |  | FALSE | FALSE
| 1.2.2. Safety and Health expectations of client | (if above Statutory requirements) |  | FALSE | FALSE
| 1.2.3. Safety and Health File - format & index |  |  | FALSE | FALSE
1.3 | Project Timescales | What are the key stages and how long will they run for?
| 1.3.1. Strategic Definition |  |  | FALSE | FALSE
| 1.3.2. Preparation and Brief |  |  | FALSE | FALSE
| 1.3.3. Concept Design |  |  | FALSE | FALSE
| 1.3.4. Developed Design |  |  | FALSE | FALSE
| 1.3.5. Technical Design |  |  | FALSE | FALSE
| 1.3.6. Construction | Planned start and finish |  | FALSE | FALSE
| 1.3.7. Handover & Close Out |  |  | FALSE | FALSE
| 1.3.8. In Use |  |  | FALSE | FALSE
| 1.3.9. Commission/ handover/ SHF |  |  | FALSE | FALSE
Note: Clarify at which of the above stages are you starting the CDM/ PCWD process
| 1.3.10. Is there any pre-existing CDM Analysis, risk register, SHF or relevant information & where? | The extent and location of existing records and plan
1.4 | Strategic Risks | What are the significant or unusual site safety and health risks or client requirements
| 1.4.1. Work involving Particular Risks (4th Sch.) |  |  | FALSE | FALSE
| 1.4.2. Strategic design intent and associated risks | Significant design assumptions and suggested work methods, sequences or other control measures; materials requiring particular precautions. |  | FALSE | FALSE
1.5 | Project Leadership
| 1.5.1. Client | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.2. Project Manager | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.3. Principal Construction Work Designer | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.4. Principal Construction Work Contractor | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.5. Cost Consultant - Quantity Surveyor | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.6. Architects | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.7. Construction Work Designer - C&S | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.8. Construction Work Designer - M&E | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.9. Construction Work Designer - Landscape | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.10. Construction Work Designer - Int. Designer | Lead Contact, Organisation and Email |  | FALSE | FALSE
| 1.5.11. Construction Work Designer - TW Designer | Lead Contact, Organisation and Email |  | FALSE | FALSE
| (continue as required) | Lead Contact, Organisation and Email |  | FALSE | FALSE
1.6 | Procurement Strategy
| 1.6.1 Procurement Methods |  | Example: Traditional/ Design & Build/ Turnkey | FALSE | FALSE
| 1.6.2. Approximate Contract Sum/ Anticipated Project Cost (if known) |  |  | FALSE | FALSE
| 1.6.3. Form of Contract (if agreed) |  | Condition of Contract / Standard form of contract choosen by client | FALSE | FALSE
1.7 | Communication Strategy
| 1.7.1. Team meetings anticipated, number, frequency, length, location etc. at each workstage. DTMs, CDM, Client etc. | Will CDM issues be considered at each DTM? Or will dedicated meetings be required? Or both? |  | FALSE | FALSE
| 1.7.2. Design Team Induction Process for CDM | Strategy brief for new design team members |  | FALSE | FALSE
| 1.7.3. Visual tools, drawings, analysis documents, review essential from all | Relevant drawing, images, photos to be included in CDM report. |  | FALSE | FALSE
| 1.7.4. Use of BIM for Safety and Health |  |  | FALSE | FALSE
| 1.7.5. Safety and Health File status | PCWD update of DTMs or Progress Meetings |  | FALSE | FALSE
1.8 | Client Duties
| 1.8.1. JKKP12 to be issued |  |  | FALSE | FALSE
| 1.8.2. Provide PCI to team |  |  | FALSE | FALSE
| 1.8.3. Welfare facilities | Assist Client and PCWC with site drawings |  | FALSE | FALSE
| 1.8.4. Site establishment and security | Site hoarding, safety nets, peripheral nets and waste chutes; site transport arrangements or vehicle movement restrictions; client's permit-to-work systems; fire precautions; emergency procedures and means of escape; 'no-go' areas or other authorisation requirements; any areas that client has designated as confined space, fragile roof, etc.; smoking and parking restrictions; construction board for displaying information such as JKKP12. |  | FALSE | FALSE
| 1.8.5. Construction phase plan prepared before construction starts | Assist client and PCWC. Minimum time to be allowed between the appointment of PCWC and instruction to commence work ont he site |  | FALSE | FALSE

## CDM1a
Project Name:
Revision Number:
Date:
1.0 Project CDM Strategy Brief - Project Team Timeline (CDM1a)
|  | Strategic Definition | Preparation and Brief | Concept Design | Spatial Coordination | Technical Design | Manufacturing and Construction | Handover | Use
LEAD | Client
Project Manager
CWD | Architect
Principal Construction Work Designer
Construction Work Designer - C&S
Construction Work Designer - M&E
Construction Work Designer - Landscape
Construction Work Designer - Int. Designer
Cost Consultant - Quantity Surveyor
Construction Work Designer - TW Designer
CWC | Principal Construction Work Contractor
Construction Work Contractor - C&S
Construction Work Contractor - M&E
(continue as required)
Note: All stakeholders, appointment and contract periods to be adjusted to suit the project strategy.

## CDM2
2.0 Site Investigation and Surveys Data Tracker (CDM2)
DRM STAGE |  |  | DRA 1 |  |  | DRA 2 | DRA 3 | HIRARC
Ref | Item | Action Owner/Notes | Date and Status | Date and Status | Date and Status | Date and Status
1 | Topographical Survey
2 | Measured Building Survey
3 | Underground Utility Survey
4 | Utility Mapping
5 | CCTV Drainage Survey
6 | Ground Penetrating Radar (GPR)
7 | Tree Survey
8 | Ecological Assessment
9 | Environmental Impact Assessment (EIA)
10 | Flood Risk Assessment
11 | Geotechnical Investigation
12 | Soil Contamination Survey
13 | Lead-based Paint or Hazardous Materials Survey
14 | Unexploded Ordinance (UXO) Clearance Check
15 | Noise Level Survey
16 | Air Quality Survey
17 | Vibration Impact Assessment
18 | Asbestos Survey
19 | Heritage Impact Assessment
20 | Cultural and Archaeological Site Survey
21 | Land Ownership and Access Verification
22 | Boundary Survey / Encroachment Assessment
23 | Building Envelope / Shadow Analysis
24 | Gazetted Heritage Building Verification
25 | Special Area Plan (Pelan Kawasan Khas) Compliance Check
26 | Visual Impact Assessment
27 | Building Height Compliance Review
28 | Forest Reserve / Environmental Buffer Clearance
29 | Land Registry Plan and Title Survey
30 | Deed, Easement, and Covenant Review
31 | Review of Local Rancangan Tempatan or Rancangan Struktur Negeri
32 | Land Use Zoning Confirmation
33 | DOSH Hazardous Substance Registration / Notification
34 | Water Supply Availability Check
35 | Solid Waste Management Plan
36 | Traffic Impact Assessment (TIA)
37 | Transport & Public Accessibility Review
38 | Travel Demand Management Strategy
39 | Construction Management Plan (CMP)
40 | Site Layout & Access Plan
41 | Fire Safety Strategy
42 | General Site Security Plan
43 | Lighting Assessment / Lux Level Study
44 | CFD / Wind Flow Analysis
45 | Sun Path and Shading Analysis
46 | Thermal Comfort Assessment
47 | Energy Strategy Report
48 | Sustainability Statement
49 | GBI / GreenRE / LEED Pre-Assessment Report
50 | Planning Justification Report
51 | Other Site or Project-Specific Assessments
52 | Detailed Design (Architectural, M&E, Structural)
53 | Detail information (full set tender drawing)
54 | Design of permanent works (earthworks, underground services, Sub-structure)
55 | Method statement
56 | Risk Register
57 | Contract documents
58 | Bill of Quantities (BQ or BOQ) – whole if any/preliminary
59 | Temporary work plan (eg. crane, scaffold, etc)
60 | Organizational chart/project team
61 | Consultant coordination

## CMD3
3.0 Schedule of Significant CDM Issues (CDM3)
Significant | Significant CDM Issues/ Description of Significant Risk * | Mitigation, Control Measures or further information | Design Issues | SHF
Risk/ Issue No. | Generic issues to be avoided | ‘So far as in reasonably practicable’ (SFARP) | Owner & Status | ✓
Not tolerable Ongoing Tolerable
1 | Site Environs and Site Establishment Strategy (incl. local features, transport corridors, pedestrian flow, welfare provisions, vehicular access, site storage, unloading, cranage etc) |  | Action Owner
D1-1-C | Presence of water table leads to water seepage and paint drop | Sub-Soil drain | C&S Engineer | ✓
D1-1-A | Stability of soil | Piling works and raft foundation | C&S Engineer, contractor. | ✓ | 2026-04-01 | 2026-12-01 | 2027-06-01
D1-1-D | Presence of water table | Piling works, raft foundation, subsoil drain, waterproofing & damp proof membrane | C&S Engineer | ✓
D1-2-D | Existing infrastrcuture/ assets on site | soil protection, surface water control, traffic control, dust control, noise control, silt trap, | Contractor | ✓
D1-2-E | access/ connection to services/ utilities | Noise control, traffic control | Contractor | ✓
1.7 | Lightning | Install earthing system and lightning arrestor | M&E Engineer | ✓
D1-4-A | Proximity to major infrastructure | early notice to residents, and road diversion, | Contractor | ✓ |  |  |  | 2026-04-01
D1-4-G | Ability to erect plant, scaffolding etc. | plan material delivery as per schedule. | Contractor | ✓
D1-3-B | Disruption to public transport | avoid peak hours delivery,One way | Contractor | ✓
2.1 | Workplace/Site Restriction | Rent the new site for TB,construct by phase to provide space for temporary building , change the cut to size or precast for materials. | C&S engineer | ✓
2.2 | Existing infrastrcuture/ assets on site | soil protection, surface water control, traffic control, dust control, noise control, silt trap, | Contractor | ✓
2.3 |  | Noise control, traffic control | Contractor | ✓
2.4 | access/ connection to services/ utilities | early notice to residents, and road diversion, | Contractor | ✓
2.5 | Ability to erect plant, scaffolding etc. | plan material delivery as per schedule. | Contractor | ✓
2.6 | Disruption to public transport | avoid peak hours delivery,One way | Contractor | ✓
2.7 | Susceptible to flooding - flooding, near to river, soft clay and high water level | Relocate site, sufficient drainage, elevate the land level, instruction to C&S for details design | C&S | ✓
2 | Site Enabling Strategy (incl. demolitions, de-contamination, remediation, temp. works etc.)
2.1 | Demolition required | proper demolision planning + method | Contractor | ✓
2.2 | Open Corridor above entrance + Hall | Introduce netting | Contractor | ✓
2.3 | Swtich Room | provide headlight + temporary exhast fan | Contractor | ✓
2.4 | Theft/malicious damage; trespas | Site Clearing and hoarding | Contractor | ✓
2.5 | Demolition required | proper demolision planning + method | Contractor | ✓
2.6 | Open Corridor above entrance + Hall | Introduce netting | Contractor | ✓
2.7 | Swtich Room | provide headlight + temporary exhast fan | Contractor | ✓
2.8 | Theft/malicious damage; trespas | Site Clearing and hoarding | Contractor | ✓
3 | Existing Building and Services Strategy (incl. above and below ground features, adjoining properties, party wall issues etc)
3.1 | Existing underground services | Need to do underground mapping using modern-technology tools | C&S engineer | ✓
3.2 | Existing roads settlement due to heavy equipments ingress and outgress | Adding inter-lockking paver to the access | C&S engineer | ✓
3.3 | Existing bulding to be demolish | Check with local authorities and communication with the neighbourhood for the demolition | contractor | ✓
3.4 | Accsess to AHU - The accsess too narrow - The impact may result in costly damage to high-value construction equipment and adversely affect essential building elements, potentially leading to structural degradation and increased project costs | Dismantle equipment to smaller parts to the designated room and install later | C&S engineer | ✓
3.5 | Working at height | To provide mobile scaffold, to provide scissor lift | contractor | ✓
3.6 | Maintainance Acsess to Roof Gutters - Accsess unsecure - Fatal | To install platform & anchorage | C&S engineer | ✓
3.7 | Inconvenience to residents | Limit working hours, wash trough, dust control, | client | ✓
3.8 | Damage to property during construction | Injection pile and smaller equipment to reduce vibration | C&S engineer | ✓
3.9 | Maintenance to a/c | Indicate the safety lifeline to the edge of roof and proper access to rooftop during design stage | contractor | ✓
4 | Maintenance to water tank | Indicate the safety lifeline to the edge of roof and proper access to rooftop during design stage | contractor | ✓
4.1 | Maintenancce to the roof gutter | Indicate the safety lifeline to the edge of roof and proper access to rooftop during design stage | contractor | ✓
4.2 | Existing building & garrage | Demolish existing building and garrage | C&S engineer | ✓
4.3 | Obstruction - Illegal Assets at proposed site - Abandoned Small Storage Area - Temporary Shared Parking - Abandoned Vehicle - Debris IMPACT - Community Retialiation, Community Assets on Site, Nearby Structure | - Report to relevant authority to get clearance on the disposal and demolation - Site Arrangement and Notification to Demolish - Public Annoucement - Demolition - Dispose abandoned cars to other place - Set exact perimeter | Contractor | ✓
4.4 | Trespassing - Illegal Entrance & Road Traffic (Existing Roadway, housing areas) IMPACT - Public Trespassing to the area | - Site Hoarding on site perimiter - Public Annoucement & Notifications - Hire Security and Safety Personnel - Provide project signages | Contractor | ✓
4.5 | Soil Stability - Land Settlement (Land Topography) IMPACT Unknown Land Condition and topography - Uneven surface and soft soil | - Site Survey - Consider impact load in design of structure frame - Use non-destructive excavations methods prior full excavation - Set to exact perimeter - Installation of piles (to refer to C&S design) | Land Surveyor/C&S | ✓
4.6 | Surrounding Hazards - Dust, Noise, Environmental contamination Nearby Community - Housing Area - Surau IMPACT - Retaliation from the community/stakeholders | - Public Annoucement to avoid public retaliation - Frequent Monitoring on environment control - Dust, Noise, Biohazard - Advanced structure installation to reduce dust works. Pre-fab structure/materials - To instruct C&S to design suitable build up method | PC | ✓
4 | Structural Works Strategy (incl. permanent, temporary & demolition requirements)
4.1 | Platform stability during working - i. Structure (double volume) ii. Roof, truss & gutter installation iii. Brick/Plastering/Wall Clading installation iv. Window installation v. Air-cond outdoor installation vi. Water tank/hose reel tank installation v. Maintenance/Repair work | saw plate, crusher run, climbing platform, skylift, change to prefabricate method, Competent person, inspection, green tag, Personal PPE (Safety Harness, safety shoes, leather glove), WAH & Scaffolding Training, | Contractor | ✓
4.2 | Falling object such as brick, tools, material, etc. where no catch platform, safety net, shelter, pedestrian walkway may cause struck by falling object during working causing injury or death | Install catch platform, safety net, shelter. | Contractor | ✓
4.3
5 | Heavy Component Movement Strategy (incl. large, heavy and awkward components, method of vertical and horizontal movement for delivery storage & placement)
5.1 | Ability to expand the facility in the future | Change new site, Safety netting 2 layer | Contractor | ✓
5.2 | Heavy and bulky elements | Limit the quantities per lifting | Contractor | ✓
5.3 | Level differences | Relocate crane at flat platform | Contractor | ✓
5.4 | Ability to expand the facility in the future | Change new site, Safety netting 2 layer | Contractor | ✓
5.5 | Site confined by adjacent road and properties - Limited workspace, restricted movement for cranes/lorry | Avoid unsafe logistics paths Plan site layout for safe movement Provide compact tools for restricted areas | Consultant | ✓
6 | Off-site & On-site manufacturing and assembly strategy (incl. prefabricated, modular, hand installed etc)
6.1 | Working at height for installation of steel truss | assemble on ground then lifting, working platform, lifting supervisor, lifting team, SOP, order suitable crane, safety harness | C&S engineer | ✓
7 | Safe working at height strategies (e.g. significant roof access, high ceilings, etc.)
7.1 | Working & maintenance at high level | Prefabrication | Contractor | ✓
7.2 | Lacking of Working platform at high | Prefabrication | Contractor | ✓
7.3 | mild steel catladder and access to manhole and catwalk | approved method statement on how to working at height, anchor point, catladder , provide appropriate training for working at height, Contractor require safety harness | Contractor | ✓
7.4 | lack of equipment / structure to maintain high bay lights | Genie lift, retracktable system for light system, PPE required for maintenance work | Contractor | ✓
7.5 | lack of safe traversing on roof | approved method statement on how to working at height, installation of lifeline, provide appropriate training for working at height, Contractor require safety harness and PPE | Designer | ✓
8 | Health Strategy (eg: excessive, dust, MSD, HAV, noise minimisation etc.)
8.1 | Heat stroke | to schedule works base on weather | client | ✓
8.2 | Surrounding occupancies | Change new site, frequent water browsing, piling to change the jack in pile | C&S, contractor | ✓
8.3 | Illegal dumping at site | Site clearing & Fogging | contractor | ✓
8.4 | Surrounding occupancies | Change new site, frequent water browsing, piling to change the jack in pile | C&S, contractor | ✓
8.5 | Hazardous materials contained in existing infra/ assets - cause health issues and rat's dieseas | -Complaint to authority to remove the rubbish - Remove/reduce unnecessary hazardous substances - Fogging - Provide Frequent RORO use/ Restrict excavation depth - Prepare a procedure to ensure all rubbish cleaned as per authority requirements | Architect / M&E | ✓
8.6 | soil contamination - from Oil, heavy metals, past industrial use, human waste | - To conduct soil testing - In case happened, to provide soil sealing/covering - To provide temporary toilet | Architect / C&S | ✓
8.7 | Surrounding Hazard - Pencawang Elektrik | Dstance of building to PE to follow authority requirement/ Buffer Zone. As per UBBL requirement | Architect | ✓
8.8 | Nearby housing areas and schools - Community complaints, health risks from dust/noise | Avoid excessive dust/noise Protect with noise barriers Schedule noisy work outside school hours | client | ✓
9 | Plant & Services design and installation strategy (e.g. location and construction issues)
9.1 | Lightning | to establish proper ligning arestor system | contractor | ✓
10 | Plant Replacement strategy (e.g. future access issues)
11 | Plant, plantrooms services + riser access and Maintenance strategy
11.1 | Emergency route | Design stage to allow access for emergency | contractor | ✓
11.2 | Backup electrical supply & emergency signage | design stage to allow design for backup supply & emergency signage | contractor | ✓
| Public utilities (TNB, water supply) located close to site - Risk of striking underground or overhead utilities | Avoid work near live utilities Assign trained personnel for utility work Insulated/ergonomic tools; redesigned work sequence to avoid live utilities; permit-to-work control for hazardous zones. | contractor | ✓
12 | Facade access, window cleaning and glass replacement strategy
13 | Phasing strategy (e.g. site, construction, occupation, etc.)
13.1 | Flood | To establish proper drainage system | C&S Engineer | ✓
13.2 | Vibration from piling or earthworks may cause cracks in neighbouring structures - Liability claims, project delays | Assign experienced operators for sensitive piling works Low-vibration piling rigs; vibration damping mats; shorter impact cycle methods | C&S Engineer | ✓
14 | Miscellaneous issues (e.g. landscaping, wellbeing, Workplace Regulations etc.)
14.1 | Theft/malicious damage / | Hoarding, guard, fencing/gate, install CCTV & warning signboard | Contractor | ✓
14.2 | Trespass / Hoarding, guard, fencing/gate, install CCTV & warning signboard | Hoarding, guard, fencing/gate, install CCTV & warning signboard | Contractor | ✓
14.3 | Lightning strike - lightning arrester & earthing system | To provide safe worker's shelters during construction period | PC | ✓
14.4 | Lightning strike - lightning arrester & earthing system | To install lightning arrester & earthing system (permanent) | M&E engineer | ✓
14.5 | Large trees on neighbouring lots - Risk of root damage to structures, falling branches | Buffer zone landscaping; battery-powered trimmers; staged trimming works. | Contractor | ✓

## CDM3a (DRA1)
3.0 Schedule of Significant CDM Issues - Detail (CDM3a)
1. Hazard Identification | [5 empty] | 2A. Risk Analysis (Ofiginal Risk) | [11 empty] | 2B. Risk Analysis (Residual Risk) |  |  | 4. Action Plan & Due Date | 5. Remarks
General Principles of Prevention (GPP)
No. | Element of design (Table 6) | Possible Design Issues / Hazards/ Constraints/ Challenges/ Problems | Elaboration (optional) | Possible Events/ Consequences/ Impacts/ Severity | Who at Risk | (L) Likelihood | (S) Severity | (R) Risk | Avoid risks | Evaluate Unavoidable Risk | Combat risk at source | Substitute | Adapt the work to the individual through design, equipment, method changes | Adapt to technical progress / engineering control | Develop a coherent overall prevention policy | Collective protective measures | Give appropriate instructions to employees | (L) Likelihood | (S) Severity | (R) Risk
D1-1-a | Stability of soil (subject to landslip) | Earthworks activities during the construction phase | Work involving excavation, filling, compaction, and grading works (1-5m soil strength - Firm CLAY) | Movement of slope | Construction workers and site personnel | 3 | 3 | 9 | NA | Conduct slope stability analysis | Provide safe slope design | Use reinforced slopes or retaining structures where slopes are unstable | Ensure safe access and working platforms on sloping ground | Install slope monitoring system and warning signage | Develop emergency response plan for slope failure | Provide barricade/guardrail and temporary retaining wall | Conduct toolbox briefing and safety induction regarding slope hazard and safe access route | 2 | 2 | 4 | Geotechnical Engineer to perform detailed slope stability analysis during design stage
D1-1b-1 | Proximity of bodies of water to project | An existing pond is present within the project boundary to be demolished during earthworks | Pond contains stored water and soft surrounding soil | Sudden water release causing flooding of excavation area | Construction workers and site personnel | 5 | 3 | 15 | Prevent working during heavy rain | Assess pond volume and discharge impact | Control water release using staged drainage / bund / gated pipe | Implement a proper drainage system (culvert or open drain) complete with a detention pond | Ensure safe access, safe distance and working platform near pond | Provide temporary pumping system & install perimeter drainage | Integrate water management into Construction Method Statement | Install guardrails near pond & provide signage and restricted access zones | Brief workers on water hazard and emergency response | 2 | 2 | 4 | Hydrology/Hydraulic Engineer
D1-1b-2 | Proximity of bodies of water to project | A detention pond is present 300m away from the project boundary (North-East) | Pond serves the Taman Tasik Air Biru residential | Earthworks increase runoff before new detention pond is completed (pollution of Tasik Biru) | Neighbouring residents/ Pollution of Tasik Biru | 4 | 5 | 20 | NA | Perform runoff estimation vs existing pond capacity | Phase earthworks and limit exposed area | Provide silt trap as a temporary detention pond | NA | Install perimeter drain, diversion channel, check dam | Include stormwater control in method statement & sequencing | Increase capacity of temporary detention pond as secondary/ double detention pond | Toolbox briefing & emergency response for heavy rain Conduct public briefing to nearby resident | 2 | 4 | 8 | Hydrology/Hydraulic Engineer | Temporary stormwater control must be in place before earthworks

## CDM3b (DRA2)
3.0 Schedule of Significant CDM Issues - Detail (CDM3b)
1. HAZARD IDENTIFICATION | [6 empty] | 2A. RISK ANALYIS (REMAINING RISK) |  |  | 3. RISK CONTROL | [8 empty] | 2B. RISK ANALYSIS (RESIDUAL RISK) |  |  | 4. Action & Due Date | 5. Remark
DESIGNER TO CONSIDER THE FOLLOWING SIGNIFICANT RISK (Table 7) |  |  | Component / Condition / Circumstances | Possible Design Issues / Hazards/ Constraints/ Challenges/ Problems | Possible Events/ Consequences/ Impacts/ Severity | Who at Risk |  |  |  | General Principles Of Prevention (GPP)
[7 empty] | L | S | R | Avoid risks | Combat risk at source | Substitute | Adapt the work to the individual through design, equipment, method changes | Adapt to technical progress / engineering control | Develop a coherent overall prevention policy | Collective protective measures | Give appropriate instructions to employees | PPE | L | S | R
D2-1-a | Fabrication | a
D2-1-b |  | b
D2-1-c |  | c
D2-2-a | Heavy lifting | a
D2-2-b
D2-2-c |  | b
3 | Confined Space | a
b
c
4 | Falling from height | a
b
c
5 | Temporary works and sequencing | a
b
c
6 | Layout | a
b
c
7 | Access for maintenance | a
b
c
8 | Health hazards | a
b
c
9 | Weather | a
b
c
10 | Emergency Route | a
b
c
11 | Others | a
b
c

## CDM3c (DRA3)
1. HAZARD IDENTIFICATION | [5 empty] | 2A. RISK ANALYIS (PURE RISK) |  |  | 3. RISK CONTROL | [7 empty] | 2B. RISK ANALYSIS (RESIDUAL RISK) |  |  | 4. Action & Due Date | 5. Remark
DESIGN ELEMENTS |  | DESIGNER TO CONSIDER THE FOLLOWING SIGNIFICANT RISK (Table 8) | Component / Condition / Circumstances | Possible Design Issues / Hazards/ Constraints/ Challenges/ Problems | Possible Events/ Consequences/ Impacts/ Severity |  |  |  | Prevention Through Design (PtD) |  |  |  |  | Control Measures
[6 empty] | L | S | R | Avoid risks | Combat risk at source | Substitute | Adapt the work to the individual through design, equipment, method changes | Adapt to technical progress / engineering control | Develop a coherent overall prevention policy | Collective protective measures | Give appropriate instructions to employees | L | S | R
1 | Construction Work Method & Technology Utilisation | a
b
2 | Temporary Works and Sequencing | a
b
c
d
f
g
h
3 | Specialist Design | a
b
c
d
f
g
h
4 | Weather | a
b
c
d
f
g
h
5 | Others | a
b
c
d
f
g
h

## CDM3d (CRA)
3.0 Schedule of Significant CDM Issues - Construction (CDM3d)
1. HAZARD IDENTIFICATION | [5 empty] | 2A. RISK ANALYIS (REMAINING RISK) |  |  | 3. RISK CONTROL | [9 empty] | 2B. RISK ANALYSIS (RESIDUAL RISK) |  |  | 4. Action & Due Date | 5. Remark
NO | WORK PROGRAM (Table 8/8a) | CONSTRUCTION ACTIVITIES (MoS/WMS/SWP) | Possible Design Issues / Hazards/ Constraints/ Challenges/ Problems | Possible Events/ Consequences/ Impacts/ Severity | Who at Risk |  |  |  | Prevention Through Design (PtD) | [5 empty] | Control Measures
[6 empty] | L | S | R | Avoid risks | Evaluate Unavoidable Risk | Combat risk at source | Substitute | Adapt the work to the individual through design, equipment, method changes | Adapt to technical progress / engineering control | Develop a coherent overall prevention policy | Collective protective measures | Give appropriate instructions to employees | PPE | L | S | R
D4-4-a
D4-4-b

## CDM4
CDM 4
DRA1
CDM4
DRA2
CDM 4
DRA 3
CPP
Capture the identified significant risks on CDM Visual Risk Analysis Drawings. Capture also other consultants significant risks
Source: Paul Bussey RIBA- A practical look at PD role

## CDM4a
4.0 CDM Option Matrix (CDM4a)
Significant | CDM Issues | Description of Options * |  |  | Analyses | [5 empty] | Choosen Option & Justification
Risk/ Issue No. | CDM issues to be evaluate | CDM possible design solutions |  |  | Option 1 |  | Option 2 |  | Option 3 |  | Selected Option | Justification
|  | Option 1 | Option 2 | Option 3 | Pros | Cons | Pros | Cons | Pros | Cons
1 | Site Environs and Site Establishment Strategy (incl. local features, transport corridors, pedestrian flow, welfare provisions, vehicular access, site storage, unloading, cranage etc)
3 | Existing Building and Services Strategy
2 | Site Enabling Strategy (incl. demolitions, de-contamination, remediation, temp. works etc.)
3 | Existing Building and Services Strategy (incl. above and below ground features, adjoining properties, party wall issues etc)
4 | Structural Works Strategy (incl. permanent, temporary & demolition requirements)
5 | Heavy Component Movement Strategy (incl. large, heavy and awkward components, method of vertical and horizontal movement for delivery storage & placement)
6 | Off-site & On-site manufacturing and assembly strategy (incl. prefabricated, modular, hand installed etc)
7 | Safe working at height strategies (e.g. significant roof access, high ceilings, etc.)
7.1 | Maintenance of atrium rooflights | Install permanent gantries and wolkways | Design rooflights that can be cleaned from below | Provide permanent anchors and hooks for rope access technicians | Eliminates the need for temporary access equipment and significant reduces risk | High initial cost and impacts the architectural aeshetics of the space | Eliminates working at height completely | Required speecialized and more expensive rooflight systems and may not be feasible for all areas | Lower cost than gantries. Aestherically discreet. Allows for safe work at height by specialist teams | still requires working at height, though with a managed system | Chosen Option 3 | Integrating maintenance hooks is most cost-effective and practical solution. Its allows for safe maintenance without compromising the design.
8 | Health Strategy (eg: excessive, dust, MSD, HAV, noise minimisation etc.)
9 | Plant & Services design and installation strategy (e.g. location and construction issues)
10 | Plant Replacement strategy (e.g. future access issues)
11 | Plant, plantrooms services + riser access and Maintenance strategy
12 | Facade access, window cleaning and glass replacement strategy
13 | Phasing strategy (e.g. site, construction, occupation, etc.)
14 | Miscellaneous issues (e.g. landscaping, wellbeing, Workplace Regulations etc.)

## CDM 5
5.0 Safety and Health File (CDM5)
| D1-1b-1 | Proximity of bodies of water to project | An existing pond is present within the project boundary to be demolished during earthworks | Pond contains stored water and soft surrounding soil | Sudden water release causing flooding of excavation area | Construction workers and site personnel | 5 | 3 | 15 | Prevent working during heavy rain | Assess pond volume and discharge impact | Control water release using staged drainage / bund / gated pipe | Implement a proper drainage system (culvert or open drain) complete with a detention pond | Ensure safe access, safe distance and working platform near pond | Provide temporary pumping system & install perimeter drainage | Integrate water management into Construction Method Statement | Install guardrails near pond & provide signage and restricted access zones | Brief workers on water hazard and emergency response | 2 | 2 | 4 | Hydrology/Hydraulic Engineer
| D1-1b-2 | Proximity of bodies of water to project | A detention pond is present 300m away from the project boundary (North-East) | Pond serves the Taman Tasik Air Biru residential | Earthworks increase runoff before new detention pond is completed (pollution of Tasik Biru) | Neighbouring residents/ Pollution of Tasik Biru | 4 | 5 | 20 | NA | Perform runoff estimation vs existing pond capacity | Phase earthworks and limit exposed area | Provide silt trap as a temporary detention pond | NA | Install perimeter drain, diversion channel, check dam | Include stormwater control in method statement & sequencing | Increase capacity of temporary detention pond as secondary/ double detention pond | Toolbox briefing & emergency response for heavy rain Conduct public briefing to nearby resident | 2 | 4 | 8 | Hydrology/Hydraulic Engineer | Temporary stormwater control must be in place before earthworks

## CDM 6
6.0 Design Risk Management - CDM Procedures for Project Teams (CDM6)

## CDM 7
7.0 CDM Health Issues Matrix (CDM7)